## Aufgabenpakete
| Automated Ordermanagement | Cutting Line Programs | Purchase Order Link & Creation | Demand Forecast [trial w/ Machine Learning] | Production Planning [xlsx upload] | Capacity Planning | Substrate Management | Automated Blocked / DRG stock usage | Stock Simulation incl. generic PP | Request Tool / SAP Upload? | Dashboard | Interface Plan4Glass | Weekly für Datenquellen und Rohbau | PSAT erstellen | Hosting & schnittstellen (technisch)
Prio | 1 | 3 | 3 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1
Arbeitspakete | Service Blueprint |  |  | Service Blueprint | Service Blueprint |  | Service Blueprint |  | Service Blueprint | Workshop zur Definition Anforderung und Lösung | Service Blueprint
| Datenquellen |  |  | Datenquellen | Datenquellen |  | Datenquellen |  | Datenquellen |  | Datenquellen
| Businesslogik |  |  | Businesslogik | Businesslogik |  | Businesslogik |  | Businesslogik |  | Businesslogik
Ansprechpartner | Alexander, Emre Mohammed (KS) |  |  | Alexander, Emre | Alexander, Emre |  | Alexander, Emre |  | Alexander, Emre | In Workshop: Alexander, Clemens, Mohammed, Bozidar, Nazila | Nazila, florian, Alexander, Clemens |  | Alexander/Emre GGF Florian für Anbindung an Grafana/Industrienet | Heinrich Thesling & felix Grawe, Ralf, Libin | Libin, Marcel
Funktionen | Automatisierte Auftragsbewertung |  |  | Breakdown auf artikelebene aus Vertriebsvorschau (Board) Maschine Learning (nice to have in zweitem Schritt) | Generierung eines Upload Templates für die produktionsprogramme Komponenten: Orderbook, Vorprodukt, Demand Forecast (weiter Kapazitäten) |  | erstellung einer Datenbank/Tabelle über Taggenaue Vorproduktbedarfe, basierend auf Order Management und Demand Forecast (Grundlage BOMs SAP) |  | Produktionsvorausschau für Zeitraum x (3 Monate) unter berücksichtigung aller Bestände plus produktion plus Zukäufe - Aufträge | Grundlegende Frage: Können wir Produktionsdaten in SAP hochladen? Dazu Workshop zu halten Informationsbereitstellung der Verfügbarkeit des Produktes in einem Dashboard (Customer Service Request Tool) | zentrae Darstellung in einem Tool, Anschließend an Vorherige Schritte als Ergebnis aus vorherigen Workshops |  | Wöchentliches Meeting, um korrekte Implementierung der Excel Lögik in Python herzustellen | Einstellen PSAT, Freigeben Flows | Dev-Server, prodserver, Berechtigungen, DIGA-intern
Für alle Punkte gelten die 3 Arbeitspakete:
Service Blueprint
Datenquellen
Businesslogik
| Planung nächste Schritte, | Alexander, Felix, Nazila, Ralf
Kurze Sprints für Gesamtprojekt
Lessons Learned aufnehmen
Definition Prozessfluss/Ablaufdiagramm (Emre / Felix)
Erstellung zentrale Ordnerstruktur

## Zeitplanung
| P | 2023 | [8 empty] | 2024
R
| I | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 | Q2 | Q3 | Q4
TOPIC | O | A | M | J | J | A | S | O | N | D
Automated Ordermanagement | 1 | Done
Cutting Line Programs | 3
Purchase Order Link & Creation | 3
Demand Forecast [trial w/ Machine Learning] | 1 | Started
Production Planning [xlsx upload] | 1
Capacity Planning | 2
Substrate Management | 1 | BOM updates started
Automated Blocked / DRG stock usage | 3
Stock Simulation incl. generic PP | 1
Request Tool / SAP Upload? | 1
Dashboard | 1
Interface Plan4Glass | 3